## SW
S.No. | Name of Employee | time axis 2021-03-31 to 2022-04-08
1 | Shivanshu | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | PCT data Extraction | PCT data Extraction | PCT data Extraction | PCT data Extraction | PCT data Extraction | PCT data Extraction | PCT data Extraction | PCT data Extraction | PCT data Extraction | huawei portal notifications for gaman sir. & PCT data extraction | wordpress contact page for Atlas website | PCT data extraction | RMS portal development | Atlas global technologies website | Atlas global technologies website | Atlas website changes + RMS | RMS portal development | RMS portal development + PCT Extraction | Atlas website + PCT extraction | Atlas website + PCT extraction | Atlas website + PCT extraction | RMS portal + PCT extraction | RMS portal + PCT extraction | RMS portal + PCT extraction | RMS portal + PCT extraction | RMS portal + PCT extraction | RMS portal + PCT extraction | RMS portal + PCT extraction | RMS portal + PCT extraction | PCT script changes for China | PCT script changes for China | PCT script changes for China | PCT script setup in laptop | PCT script setup in laptop | PCT script changes | PCT script setup + contact form configuration | System configuration for PCT | System configuration for PCT | PCT script optimization & running on multiple instances | PCT extraction | PCT extraction | PCT extraction | PCT extraction | PCT extraction | PCT extraction | PCT extraction | Leave | PR automation feasibility | Leave | PR automation feasibility | Effepro portal | Effepro portal | Effepro portal | Effepro portal | Sample search portal | Sample search portal | Sample search portal | Sample search portal | Sample search portal | Sample search portal | Connect2care app | Sample search portal | Sample search portal | Sample search portal | Effepro projects | Effepro projects | Effepro projects | Effepro projects | Effepro projects | Effepro projects | Effepro projects | dtSearch Tool testing | dtSearch Tool | Effepro projects | Leave | 3gpp data extarct | 3gpp data extarct | Sample Search | Sample Search | Effepro multiple projects | Effepro multiple projects | 3gpp FTP data download | 3gpp FTP data download | Leave | Sample Search + 3gpp data download | Sample Search | Leave | Leave | Sample Search | Leave | Sample Search | Leave | Sample Search | Sample Search | Sample Search | Sample Search | Sample Search | Sample Search | dtSearch | dtSearch | dtSearch | dtSearch | dtSearch | dtSearch data indexing | dtSearch data indexing | 3GPP incremental data download | WIPO extraction | WIPO extraction | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Python Automation web setup | Python Automation web setup | Python Automation web setup | Python Automation web setup | Python Automation web setup | Python Automation web setup | XML data Extraction | XML data Extraction | XML data Extraction | XML data Extraction | XML data Extraction | XML data Extraction | XML data Extraction | XML data Extraction | XML data Extraction | Leave | Leave | RMS,Trademark | RMS,Trademark | RMS,Trademark | RMS,Trademark | RMS,Trademark | RMS,Trademark | RMS,Trademark | Leave | Leave | Client Portal | Client Portal | Client Portal | Client Portal | Client Portal | Client Portal | Leave | Leave | Effectual Website | Effectual Website | Effectual Website | Effectual Website | Effectual Website | Effectual Website | Effectual Website | Effectual Website | Effectual Website | Effectual Website | Effectual Website | Effectual Website | Effectual Website | Leave | Effectual Website | Effectual Website | Effectual Website | Effectual Website | DT Search | DT Search | DT Search | Leave | DT Search | DT Search | Leave | DT Search | DT Search | DT Search | DT Search | DT Search | DT Search | DT Search | DT Search | DT Search | DT Search | DT Search | Security Score | Security Score | Security Score | DT Search | Leave | WIPO data extraction | WIPO data extraction | DT search | DT search | DT search | DT search | DT search | DT search | DT search | DT search | Leave | DT search | DT search | Effectual Website | Effectual Website | Effectual Website | Effectual Website | Leave | Leave | Effectual Website | Effectual Website | Effectual Website | Effectual Website | Effectual Website | leave | Effectual Website | Effectual Website | Effectual Website | Effectual Website | Effectual Website | Effectual Website | Effectual Website | dt search | dt search | dt search | dt search | dt search | dt search | dt search | Effectual website | Effectual website | Effectual website | Effectual website | Effectual website | Leave | Effectual website | Effectual website | Effectual website | leave | Effectual website
2 | Pramod | 1.Report Automation (Query Synonyms) Delivered for Testing 2.PCT Extraction proxy testing | 1.Report Automation (Query Synonyms) Delivered for Testing(asked Anoop for testing status.) 2.PCT Extraction proxy testing | 1.Report Automation (Query Synonyms) Delivered for Testing(asked Anoop for testing status.) 2.PCT Extraction proxy testing | Leave | 1.Report Automation(changes suggested by anoop) | 1.Report Automation(changes suggested by anoop) | 1.Report Automation(changes suggested by anoop) | 1.Report Automation(changes suggested by anoop) Expected completion date - 13/4/2021 | 1.Report Automation(changes suggested by anoop) Expected completion date - 13/4/2021 | 1.Report Automation(Delivered Anoop for testing) | 1.Report Automation(Delivered Anoop for testing) | 1.Report Automation(Delivered Anoop for testing) | 1.Report Automation(Delivered Anoop for testing) | Leave | Leave | Leave | Leave | 1.Report Automation | 1.Report Automation | 1.Report Automation | Leave | Leave | Leave | Leave | Leave | Leave | Report Automation | PCT Extraction | PCT Extraction | PCT Extraction | Report automation bugs | Report automation bugs | Report automation bugs | Report automation bugs | Report automation bugs | Report automation bugs | Report automation bugs | Report automation bugs | Report automation bugs | Report automation testing | Report automation testing | Report automation testing | Report automation testing | Report automation testing | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Joginder Transpose macro | Joginder Transpose macro | PCT extraction | PCT extraction | PCT extraction | PCT extraction | PCT extraction | PCT extraction | PCT extraction | PCT extraction | PCT extraction | PCT extraction | PCT extraction | PR automation | Report automation changes | Leave | Leave | Report automation changes | Report automation changes | Report automation changes | PR automation | PR automation | PR automation | PR automation | Leave | PR automation | PR automation | PR automation | PR automation | Leave | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Leave | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | Report automation changes | PR automation | PR automation | PR automation | PR automation | PR automation | PR automation | PR automation-Phase 2( read pdf and get status of Refusel or Oppositon) | PR automation pdf OCR | PR automation pdf OCR | PR automation | PR automation | PR automation | PR automation-Phase 2( read pdf and get status of Refusel or Oppositon) | PR automation-Phase 2( read pdf and get status of Refusel or Oppositon) | PR automation-Phase 2( read pdf and get status of Refusel or Oppositon) | Leave | Leave | PR automation-Phase 3(Error handling) | PR automation-Phase 3(Error handling) | PR automation-Phase 3(Error handling) | PR automation-Phase 3(Making Executable file) | PR automation-Phase 4(Testing EXE with different scenario) -Task completed, Sending today for testing & feedback | Outlook mail Follow Up macro | Outlook mail Follow Up macro | Outlook mail Follow Up macro | Outlook mail Follow Up macro | Outlook mail Follow Up macro | Outlook mail Follow Up macro | Outlook mail Follow Up macro | Leave | Outlook mail Follow Up macro | Outlook mail Follow Up macro | Outlook mail Follow Up macro changes - Change from Reply mail to Forward with previous attachements. - Changing subject of forwarded mail. | Leave | Leave | Leave | Fixing PR Exe compatibility issue in different system | Fixing PR Exe compatibility issue in different system | Mapping API jason data & write in Excel | Mapping API jason data & write in Excel | Mapping API jason data & write in Excel | Mapping API jason data & write in Excel | Mapping API jason data & write in Excel | PR data Extraction with pdf OCR in python | Leave | Adding changes in Outlook mail macro suggested by jogindera | Patent Ranking | Patent Ranking & Adding changes in Outlook mail macro suggested by jogindera | Leave | Patent Ranking & PR data Extraction with pdf OCR in python | Adding changes in PR data Extraction macro | Adding changes in PR data Extraction macro | Patent Ranking | Patent Ranking | Fixing PR macro | Fixing PR macro | Leave | Fixing PR macro/Patent Ranking | Leave | Patent Ranking | Patent Ranking | Patent Ranking | Patent Ranking | Patent Ranking | Patent Ranking | Patent Ranking | Leave | Leave | Leave | Patent Ranking |  | Trademark | Patent Ranking | Patent Ranking | Patent Ranking | Patent Ranking | Leave | Leave | Patent Ranking | Trademark | Patent Ranking | Leave | Trademark API | Trademark API | Trademark API | Leave | Trademark data extraction & Trademark API | Trademark API | Trademark API | Trademark tool Fixing error in summary | Trademark tool Fixing error in summary | Trademark tool Fixing error in document title | Trademark tool Deploy on cloud | Trademark tool Deploy on cloud | Leave | Trademark tool Data extraction | Leave | Trademark tool Data extraction & fixing link error | Trademark tool Data extraction & Create multiple instance | Trademark tool Data extraction & Create multiple instance | Trademark tool Data extraction & Create multiple instance | Trademark tool Data extraction & Create multiple instance | Trademark tool Data extraction & Create multiple instance | Trademark tool Data extraction & Create some new account to deploy code on new could accout. | Trademark tool Data extraction & wipo API. | Trademark tool Data extraction & wipo API. | Trademark Exe based | Trademark Exe based | Trademark Exe based | Trademark Exe based | Leave | Trademark Exe based | Trademark Exe based | Trademark Exe based | Trademark Exe based | Trademark Exe based | Leave | HML | Ui HML patent Ranking | Ui HML patent Ranking | Ui HML patent Ranking | Ui HML patent Ranking | Ui HML patent Ranking | Ui HML patent Ranking | Ui HML patent Ranking | leave | leave | leave | Ui HML patent Ranking | Ui HML patent Ranking | Outlook automation & HML deploying to server | Outlook automation | HML | HML | HML/Outlook automation | Fixing Error while deploying on Amazon server | leave | leave | leave | HML/fixing error in Outlook Automation | HML ranking new changes in logic | HML ranking new changes in logic | HML ranking new changes in logic | HML ranking new changes in logic | HML ranking new changes in logic | HML ranking new changes in logic | HML ranking new changes in logic | HML ranking new changes in logic | HML ranking new changes in logic | HML ranking new changes in logic | updating mail send macro
3 | Paras | EffeFlow Work | EffeFlow Work | EffeFlow Work | Leave | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | Effelow client guidelines | Effelow client guidelines | Effelow client guidelines | Effelow client guidelines | Effelow client guidelines | Leave | Leave | Effelow client guidelines | Effelow client guidelines | Effelow client guidelines | Effelow client guidelines | Effelow client guidelines | Effelow client guidelines | Effelow client guidelines | Effeflow filters | Effeflow filters | Effeflow filters | Effeflow filters | Effeflow filters | Effeflow filters | Effeflow filters | Effeflow filters | Effeflow filters | Effeflow filters | Project Coloring | Project Coloring | Project Coloring | Project Coloring | Project Coloring | Client Guidelines | Client Guidelines | Client Guidelines | Client Guidelines | Client Guidelines | Client Guidelines | Effeflow testing | Effeflow testing | Effeflow testing | Effeflow testing | Effeflow testing | Effeflow testing | Effeflow testing | Effeflow testing | Effeflow testing | Effeflow testing | Effeflow testing | Effeflow testing | Effeflow testing | Effeflow testing | Effeflow testing | Effeflow testing | Effeflow testing | Effeflow testing | PCT extraction | PCT extraction | PCT extraction | PCT extraction | PCT extraction | PCT extraction | PCT extraction | PCT extraction | Effeflow Timesheet | Effeflow Timesheet | Effeflow Timesheet | Effeflow Timesheet | Effeflow Timesheet | Effeflow Timesheet | Effeflow Timesheet | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Leave | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Leave | Effeflow | Effeflow | Effeflow | Effeflow | Leave | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Leave | Effeflow | Effeflow | Effeflow | Effeflow | Leave | Leave | Leave | Leave | Leave | Leave | Effeflow | Effeflow | Leave | Leave | Leave | Leave | Leave | Leave | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Leave | Effeflow | Effeflow | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Leave | Leave | Effeflow | Effeflow | Effeflow | Effeflow | Mailchimp Template Design ¦ Effeflow | Mailchimp Template Design ¦ Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Effeflow | Leave | Leave | Leave | Leave | Leave | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | Leave | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | leave | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work | EffeFlow Work/Effectual Website | EffeFlow Work/Effectual Website | EffeFlow Work/Effectual Website | EffeFlow Work/Effectual Website | EffeFlow Work/Effectual Website | EffeFlow Work/Effectual Website | EffeFlow Work/Effectual Website | EffeFlow Work / Patent idea website | EffeFlow Work / Patent idea website | EffeFlow Work / Patent idea website | EffeFlow Work / Patent idea website | Leave | EffeFlow Work / Patent idea website | EffeFlow Work / Patent idea website | EffeFlow Work / Patent idea website | EffeFlow Work / Patent idea website | EffeFlow Work / Patent idea website | EffeFlow Work / Patent idea website
| Tasks | 2021-03-31: Tentetive Deadline
Shivanshu | Effectual website | 2021-03-31: 2022-03-02
| Sandeep team website | 2021-03-31: 2022-03-09
| HML | 2021-03-31: 2022-03-04
Pramod | HML
| Wipo api based (jogindra) | 2021-03-31: 2022-03-13
| Trademark | 2021-03-31: Need 2 more days-On hold now
Paras | EffeFlow Work | 2021-03-31: 2022-02-25

## Task & Deadlines
| Tasks | Tentetive Deadline | Update-1 | Tentetive Deadline with Update-1 | Update-2 | Tentetive Deadline with Update-2
Shivanshu | Effectual website | 2022-03-02 | Effectual Wbsite | 2022-04-01
| Sandeep team website | 2022-03-09
| HML | 2022-03-04 | logic for HML according to score | 2022-03-24 | more presentable UI & impliment HML new logics | 2022-03-31
Pramod | HML
| Wipo api based (jogindra) | 2022-03-13
| Trademark | Need 2 more days-On hold now
Paras | EffeFlow Work | 2022-02-25 | Effeflow -client list & Patent idea website | 2022-03-31